## Sheet1
Team 47 Product Backlog
Features | Initial Estimates (hours) | Adjust Factor | Adjust Estimate | 1 | 2 | 3
Register & Login Page | 10 | 0.5 | 15
Admin Account | 5 | 0.5 | 7.5
Create Multiple Accounts | 5 | 0.5 | 7.5
User Profile | 3 | 0.5 | 4.5
Deposits | 5 | 0.5 | 7.5
Withdrawals | 1 | 0.5 | 1.5
Transaction History | 10 | 0.5 | 15
Spending Catergory Report | 15 | 0.5 | 22.5
Income Source Report | 15 | 0.5 | 22.5
Cash Flow Reports | 15 | 0.5 | 22.5
Account Listing Report | 15 | 0.5 | 22.5
Transaction History Report | 15 | 0.5 | 22.5
Total: | 114 |  | 171